## Sheet1
Dates |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17
|  |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
|  |  | 2019-01-14 | 2019-01-15 | 2019-01-16 | 2019-01-17 | 2019-01-18 | 2019-01-19 | 2019-01-20 | 2019-01-21 | 2019-01-22 | 2019-01-23 | 2019-01-24 | 2019-01-25 | 2019-01-26 | 2019-01-27 | 2019-01-28 | 2019-01-29 | 2019-01-30 | 2019-01-31 | 2019-02-01 | 2019-02-02 | 2019-02-03 | 2019-02-04 | 2019-02-05 | 2019-02-06 | 2019-02-07 | 2019-02-08 | 2019-02-09 | 2019-02-10 | 2019-02-11 | 2019-02-12 | 2019-02-13 | 2019-02-14 | 2019-02-15 | 2019-02-16 | 2019-02-17 | 2019-02-18 | 2019-02-19 | 2019-02-20 | 2019-02-21 | 2019-02-22 | 2019-02-23 | 2019-02-24 | 2019-02-25 | 2019-02-26 | 2019-02-27 | 2019-02-28 | 2019-03-01 | 2019-03-02 | 2019-03-03 | 2019-03-04 | 2019-03-05 | 2019-03-06 | 2019-03-07 | 2019-03-08 | 2019-03-09 | 2019-03-10 | 2019-03-11 | 2019-03-12 | 2019-03-13 | 2019-03-14 | 2019-03-15 | 2019-03-16 | 2019-03-17 | 2019-03-18 | 2019-03-19 | 2019-03-20 | 2019-03-21 | 2019-03-22 | 2019-03-23 | 2019-03-24 | 2019-03-25 | 2019-03-26 | 2019-03-27 | 2019-03-28 | 2019-03-29 | 2019-03-30 | 2019-03-31 | 2019-04-01 | 2019-04-02 | 2019-04-03 | 2019-04-04 | 2019-04-05 | 2019-04-06 | 2019-04-07 | 2019-04-08 | 2019-04-09 | 2019-04-10 | 2019-04-11 | 2019-04-12 | 2019-04-13 | 2019-04-14 | 2019-04-15 | 2019-04-16 | 2019-04-17 | 2019-04-18 | 2019-04-19 | 2019-04-20 | 2019-04-21 | 2019-04-22 | 2019-04-23 | 2019-04-24 | 2019-04-25 | 2019-04-26 | 2019-04-27 | 2019-04-28 | 2019-04-29 | 2019-04-30 | 2019-05-01 | 2019-05-02 | 2019-05-03 | 2019-05-04 | 2019-05-05 | 2019-05-06 | 2019-05-07 | 2019-05-08 | 2019-05-09 | 2019-05-10
Assesment |  |  | Week 1 F: Oneon-one-check-in; Week 2 F: Support lab; Week 3 F: Critique/ Playtest; Week 4 F: ASSESMENT; Week 5 F: One-one-check-in; Week 6 M: READING WEEK; Week 7 F: Support lab; Week 8 F: Critique/ Playtest; Week 9 F: Support lab; Week 10 F: One-on-one-check-in; Week 11 F: Support lab; Week 17 F: DEADLINE
Milestones |  |  | Week 1 M: CLASSES FOR OBJECTS: We haven't really written dwon the hours; Week 4 M: OBJECTS IN SPACE: * star system * adding the lighting * all of the classes together; Week 6 M: PROTOTYPE A; Week 9 M: PROTOTYPE B; Week 12 M: PROTOTYPE C; Week 14 M: PROTOTYPE D
TASKS - Alex | Coding |  | Week 1 F: planets classes; Week 2 F: Star system; Week 3 T: Star system; Week 5 F: classes together; Week 6 M: saturn -ring; Week 7 T: saturn -ring; Week 8 W: fixing images and the efficiency; Week 8 T: camera fixing; Week 8 F: fixing camera/playtest; Week 9 T: camera fixing; Week 9 W: camera fixing; Week 9 F: camera fixing; Week 10 F: rings to the planets; Week 13 T: updating position; Week 13 F: updating position of the planet; Week 13 S: camera set up; Week 14 M: click on the mouse; Week 14 T: cleaning the code; Week 14 W: cleaning/merging; Week 14 T: merging the code; Week 14 F: updating the camera position; Week 15 M: added instructions; Week 15 T: one line for planets; Week 16 T: fixing the oneline; Week 16 T: button class; Week 16 F: fixing the position and description; Week 16 S: fixing th ebugs; Week 17 T: cleaning the code; Week 17 W: cleaning the code
| Extra staff |  | Week 4 T: assesment; Week 4 F: asessment; Week 5 M: Aded .gitignore; Week 7 T: orbits + code organisation; Week 8 S: assesment; Week 8 S: assesment; Week 9 M: assesment; Week 9 F: assesment; Week 14 W: adding rings to planets; Week 14 T: users opinion; Week 15 M: tried to make a panel class; Week 16 T: adding button class; Week 17 M: writing the report; Week 17 T: writing the report; Week 17 T: report; Week 17 F: report
| Organisation |  | Week 1 M: planets-distance-sketch; Week 3 W: Gitlab; Week 3 T: Gitlab; Week 4 M: hours - Excel sheet; Week 4 T: Gitlab; Week 5 M: Gitlab - merging; Week 5 F: gitlab; Week 7 T: gitlab; Week 7 T: gitlab; Week 9 W: gitlab; Week 9 F: gitlab; Week 11 M: planning; Week 12 F: researching how to update planets position; Week 13 T: planning; Week 14 T: gitlab; Week 14 F: hours, report-plan; Week 16 F: organisation, gitlab; Week 17 T: git; Week 17 T: git | HOURS ALEX | TOTAL
HOURS | Alex | C | Week 1 F: 3; Week 2 F: 2; Week 3 T: 1; Week 5 F: 1; Week 6 M: 2; Week 7 T: 4; Week 8 W: 3; Week 8 T: 4; Week 8 F: 3; Week 9 T: 1; Week 9 W: 3; Week 9 F: 3; Week 10 F: 1; Week 13 T: 3; Week 13 F: 7; Week 13 S: 4; Week 14 M: 4; Week 14 T: 1; Week 14 W: 3; Week 14 T: 0.5; Week 14 F: 4.5; Week 15 M: 2; Week 15 T: 2; Week 16 T: 0.5; Week 16 T: 3; Week 16 F: 4; Week 16 S: 6; Week 17 T: 3; Week 17 W: 3 | 81.5 | 146.1
|  | E | Week 4 T: 2; Week 4 F: 2; Week 5 M: 1; Week 7 T: 3; Week 8 S: 0.5; Week 8 S: 0.5; Week 9 M: 3; Week 9 F: 0.5; Week 14 W: 2; Week 14 T: 0.1; Week 15 M: 3; Week 16 T: 3; Week 17 M: 6; Week 17 T: 4; Week 17 T: 8; Week 17 F: 4 | 42.6
|  | O | Week 1 M: 1; Week 3 W: 2; Week 3 T: 3; Week 4 M: 1.5; Week 4 T: 0.5; Week 5 M: 1.5; Week 5 F: 2; Week 7 T: 1; Week 7 T: 1; Week 9 W: 0.1; Week 9 F: 0.1; Week 11 M: 1; Week 12 F: 3; Week 13 T: 1; Week 14 T: 0.2; Week 14 F: 1; Week 16 F: 1; Week 17 T: 1; Week 17 T: 0.1 | 22
TASKS - Zami | Coding |  | Week 1 W: Cam and Lighting; Week 1 T: Sun Class; Week 2 T: Finished Blackhole; Week 2 F: Gave and received feedback; Week 3 W: Set texture; Week 3 F: Submitted qritique playtest; Week 4 M: Added Blackhole to main programe; Week 4 F: Made sun Glow; Week 5 T: Material for sun & planet; Week 5 T: All cam movement; Week 7 F: 1 to 1 feedback + marks; Week 8 M: Skybox Concept modeled; Week 8 F: Fixed BH memory leak; Week 9 F: Set test UI; Week 11 M: Found Cockpit png; Week 11 F: planned alt UI; Week 12 W: Photoshopped Cockpit Image to fit project; Week 13 T: Planned and Implemented Button layout; Week 13 S: Used new Image; Week 14 T: Implemented new UI; Week 14 W: Fixed UI Resolution Problem; Week 15 M: Researched 3D Models; Week 15 T: Added hollogram and rotations; Week 16 T: Added Descripions; Week 17 M: Added Sound Effects; Week 17 T: Added Moon to Earth
| Extra staff |  | Week 6 M: problem with Git repo; Week 6 T: problem with Git repo; Week 6 W: problem with Git repo; Week 6 T: problem with Git repo; Week 6 F: problem with Git repo; Week 7 M: problem with Git repo; Week 7 T: problem with Git repo; Week 7 W: problem with Git repo; Week 7 T: problem with Git repo; Week 7 F: Got git Fixed; Week 8 M: Fixed Blackhole issue; Week 8 T: Fixed git Issue; Week 8 F: Tried Star Pointers; Week 9 F: Fixed Star Pointer; Week 15 T: Hologram positioning; Week 16 T: Added Tokenizer; Week 17 M: Reserch Moon Rot; Week 17 T: Fixed Moon Rotation
| Organisation |  | Week 3 T: Created git branch; Week 4 T: pushed to gitlab; Week 5 T: Pushed to Git branch; Week 8 T: Pushed to Gitlab; Week 9 F: pushed to gitlab; Week 14 T: pushed to gitlab; Week 16 T: Pushed to gitlab; Week 17 T: Pushed to Git | HOURS ZAMI | TOTAL
HOURS | Zami | C | Week 1 T: 0.5; Week 2 T: 4; Week 2 F: 1.5; Week 3 W: 0.35; Week 4 M: 2; Week 4 F: 0.1; Week 5 T: 0.4; Week 5 T: 3; Week 8 M: 3; Week 8 F: 3; Week 9 F: 1.3; Week 11 M: 0.3; Week 11 F: 5; Week 12 M: 6; Week 13 M: 4; Week 13 S: 0.15; Week 14 T: 4; Week 14 W: 1; Week 15 M: 2; Week 15 T: 4; Week 16 T: 5; Week 17 M: 2; Week 17 T: 8 | 60.6 | 107.8
|  |  | Week 6 M: 15; Week 7 M: 8; Week 8 M: 4; Week 8 F: 2; Week 9 F: 0.3; Week 15 T: 2; Week 16 T: 1.3; Week 17 M: 4; Week 17 T: 4 | 40.6
|  | O | Week 3 T: 5; Week 5 T: 0.1; Week 8 T: 0.2; Week 9 F: 0.2; Week 14 T: 0.4; Week 16 T: 0.3; Week 17 T: 0.4 | 6.6